Constructing a Network - Example

For this example you will draw a network for producing a new advertising campaign.  Here are the tasks:

- A – plan the advertising campaign;

- B – make a TV video;

- C – design a poster;

- D – test market the TV video;

- E – test the suitability of the poster;

- F – present campaign to the board of directors;

- G – communicate the campaign to all company personnel.

| Tasks | Order/Dependency | Duration (Days) |
| --- | --- | --- |
| A | Must be done first | 4 |
| B | Can only start when A is completed | 6 |
| C | Can only start when A is completed | 7 |
| D | Can only start when B is completed | 8 |
| E | Can only start when C is completed | 10 |
| F | Can only start when D and E are completed | 9 |
| G | Can only start when D, E and F are completed | 5 |

Draw a critical path analysis diagram to show ESTs and LFTs of the tasks involved in producing a new advertising campaign.

When you have completed your diagram, fill in the blanks in this table to detail the float time:

| Task | Duration | EST | LFT | Total Float |
| --- | --- | --- | --- | --- |
| A | 4 | 0 | 4 |  |
| B | 6 |  |  |  |
| C | 7 |  |  |  |
| D | 8 |  |  |  |
| E | 10 |  |  |  |
| F | 9 |  |  |  |
| G | 5 |  |  |  |

Next create a Gantt Chart then a Resource Histogram to represent this.