## Slide 2
Key Words
Gantt Charts and
Resource Histograms
Precedence
Heuristic
Levelling
Cascade
Float
Fluency: Recall key elements of a critical path
Reasoning: Utilise a Gantt Chart and Resource Histograms to display activities
Problem Solving: Improve a resource histogram by using resource levelling
Define the key words

## Slide 3: Knowledge Check Fluency
Draw an activity network for the following information

## Slide 4: Knowledge Check - ANSWERS Fluency

## Slide 5: Knowledge Check 2 Fluency
Draw an activity network, complete the table and identify the critical path
Activity | Duration | Immediate Predecessor | Float
A | 2 | - | 
B | 3 | - | 
C | 4 | A,B | 
D | 2 | B | 
E | 4 | C | 
F | 2 | C,D | 

## Slide 6: Knowledge Check 2 Fluency
Critical path is BCE

## Slide 7: Knowledge Check - ANSWERS Fluency
Activity | Duration | Immediate Predecessor | Float
A | 2 | - | 1
B | 3 | - | 0
C | 4 | A,B | 0
D | 2 | B | 2
E | 4 | C | 0
F | 2 | C,D | 2

## Slide 8: Gantt Charts Reasoning
Gantt charts are also called Cascade charts.
You draw activities against a time scale
The bars are solid for the length of the activity
If there is a float, this is added at the end but not shaded in
Critical activities are therefore only a solid bar

## Slide 9: Gantt Charts Reasoning
You can draw the critical activities along the bottom and touching to create a critical path
Duration
Float

## Slide 10: Resource Histograms Reasoning
A resource histogram helps to display the number of workers on activities at any given moment
You must remember if activities have others that must occur first
The height of the bar is the number of workers and the length is the duration

## Slide 11: Complete the constructing a network activity
Challenge: What would you do if you only had 4 workers available to employ at any given time?
Practice: Move onto question one of the exam questions

## Slide 12: Resource Levelling Problem Solving
Resource levelling is employing a heuristic approach (you simply try to find the optimal solution through observation)
Consider the floats if you are asked to keep the project within the minimum time
If a limit is placed on the number of workers then the duration of the project is likely to increase

## Slide 13
The values in brackets represent the number of workers required for each activity
Draw a resource histogram assuming that each activity starts as soon as possible.
How many workers are needed?

## Slide 14: Resource Levelling Problem Solving
The project requires 6 workers

## Slide 15: Resource Levelling Problem Solving
You can delay D, so the project can be completed by 5 workers

## Slide 16: Resource Levelling Problem Solving
The only activities that could be carried out simultaneously with 4 workers are B and C so the activity would now take 36 days, which is an extension of 9 days.
Now complete question 2 of the exam questions

## Slide 17: Plenary – State your confidence with each skill
Calculate the earliest and latest start and finish times for an activity network
Draw a Gantt chart for a project
Draw a resource histogram with every activity starting as early as possible
Use resource levelling to reschedule activities to minimise the number of workers needed
Use resource levelling to reschedule a project with extended duration when the number of workers is limited
What will you do to improve?

## Slide 18: Homework
Complete Chapter 4.3 questions and self assess